## Sheet1
| Start Date | Completed | Remaining
Investigate the Google API for retrieving emails | 2013-02-15 | 2 | 5
Create the Desktop Application | 2013-02-22 | 0 | 14
Write basic python scripts to run on the client. | 2013-02-22 | 0 | 14
Start and EC2 Instance and write the backend for it to be able to handle Google API calls | 2013-03-01 | 0 | 35
Configure how to network the EC2 and client computers | 2013-03-01 | 0 | 35
Integrate SQS and SNES with the EC2 instance | 2013-03-14 | 0 | 14
Put the project together and fix bugs | 2013-04-05 | 0 | 14